## Sheet1
Product Backlog sample for Social media application
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | User Registration & Authentication | User Management | As a user, I want to securely register and log in to the platform so that I can donate or receive food. | Must | In Progress | 1. Users can register using email and password. 2. Secure login with encrypted credentials. | Secure password storage, email verification, and role-based access. | Response time for authentication should be under 2 seconds. | 5 days | 4 days
2 | Food Donation Management | Food Handling | As a donor, I want to list the type and quantity of food I want to donate so that NGOs can pick it up. | Must | Pending | 1. Users can add food details (type, quantity, pickup time). 2. NGOs can view available donations. | Food listing form, real-time update on donation status. | Data consistency and quick response times for listing updates. | 7 days
3 | NGO Food Request System | Request Management | As an NGO, I want to browse available food donations and request pickup so that I can distribute it to the needy. | Must | Backlog | 1. NGOs can browse available donations. 2. NGOs can place requests for pickup. | NGO dashboard with filter options, request submission feature. | System should handle multiple NGO requests without delays. | 6 days
4 | Delivery Partner Management | Logistics & Delivery | As a delivery partner, I want to accept delivery requests so that I can transport food to NGOs. | Should | Ready for Dev | 1. Delivery partners can register and accept requests. 2. Pickup and drop details are visible. | Delivery personnel role, order tracking feature. | Delivery tracking should be updated in real-time. | 8 days
5 | Chatbot Assistance | User Support | As a user, I want chatbot support so that I can get assistance with donations and requests. | Could | Backlog | 1. Users can interact with a chatbot for common queries. 2. Chatbot can guide users through food donation and requests. | AI-based chatbot, basic FAQs, and interactive responses. | Chatbot should provide responses in under 2 seconds. | 5 days
6 | Admin Dashboard | Admin Management | As an admin, I want a dashboard to manage food donations and NGO requests so that I can track and optimize distribution. | Must | Pending | 1. Admins can view, approve, and reject food donation requests. 2. Real-time tracking of food distribution. | Admin dashboard with analytics and filtering options. | Dashboard should load under 3 seconds. | 6 days
7 | User Profile & History | User Management | As a user, I want to view my donation and request history so that I can track my contributions. | Should | Backlog | 1. Users can view past donations and requests. 2. Data visualization for contribution impact. | User profile section with donation/request history. | Data retrieval should be under 2 seconds. | 5 days
8 | Automated Matching System | Food Handling | As a system, I want to automatically match donors with nearby NGOs so that food is distributed efficiently. | Must | In Progress | 1. Donations are automatically assigned to NGOs based on location and demand. 2. Users receive notifications of matched donations. | Matching algorithm, real-time notifications. | Matching process should take less than 5 seconds. | 7 days | 3 days
9 | Reporting & Analytics | Admin Management | As an admin, I want detailed reports on food donations and distribution so that I can measure the impact. | Should | Backlog | 1. Generate reports on food saved, distributed, and impacted users. 2. Data export options (CSV, PDF). | Data visualization, export functionality. | Reports should generate within 5 seconds. | 6 days
10 | Multi-Language Support | User Experience | As a global user, I want to use the platform in my preferred language so that I can navigate easily. | Could | Backlog | 1. Users can switch between multiple languages. 2. Language settings are saved in user preferences. | Translation support for UI and chatbot responses. | Language switch should take effect instantly. | 5 days